# 1. Overview of Implementation Status

## Financial Performance of the Sectors in €

| SMSC | EU allocation | Contracted (%) | Disbursed (%) | Co-financing | Contracted (%) | Disbursed (%) |
| --- | --- | --- | --- | --- | --- | --- |
| JHA FM 2001 | 1 035 000 | 99.47 | 85.62 | 75 000 | 72.19 | 72.19 |
| JHA FM 2002 | 11 169 998 | 82.79 | 39.18 | 2 435 907 | 75.82 | 27.90 |
| JHA FM 2003 | 13 289 998 | 15.01 | 9.40 | 2 701 000 | 8.01 | 8.01 |
| JHA TF 2004 | 1 980 000 | 0.00 | 0.00 | 700 000 | 0.00 | 0.00 |
| JHA Total 2001 - 2004 | 27 474 996 | 44.59 | 23.65 | 5 911 907 | 35.81 | 16.07 |
| INT FM 2001 | 4 993 000 | 96.43 | 86.18 | 690 000 | 88.08 | 82.86 |
| INT FM 2002 | 6 781 000 | 98.69 | 58.97 | 1 200 000 | 93.35 | 88.79 |
| INT FM 2003 | 7 106 887 | 15.55 | 3.38 | 1 561 000 | 0.00 | 0.00 |
| INT TF 2004 | 4 325 000 | 0.00 | 0.00 | 374 500 | 0.00 | 0.00 |
| INT Total 2001 - 2004 | 23 205 887 | 54.46 | 36.88 | 3 825 500 | 45.17 | 42.80 |
| AGR FM 2001 | 405 000 | 99.03 | 86.03 | 0 | 0.00 | 0.00 |
| AGR FM 2002 | 8 886 000 | 96.71 | 65.74 | 8 272 000 | 97.29 | 76.40 |
| AGR FM 2003 | 8 590 000 | 9.73 | 4.82 | 1 285 000 | 8.27 | 0.00 |
| AGR TF 2004 | 4 455 000 | 0.00 | 0.00 | 755 000 | 0.00 | 0.00 |
| AGR Total 2001 - 2004 | 22 336 000 | 44.01 | 29.57 | 10 312 000 | 79.08 | 61.29 |
| ENV FM 2001 | 1 023 786 | 99.95 | 79.73 | 0 | 0.00 | 0.00 |
| ENV FM 2002 | 5 540 000 | 91.42 | 52.67 | 270 000 | 90.81 | 80.73 |
| ENV FM 2003 | 3 864 999 | 30.19 | 11.80 | 546 000 | 22.41 | 0.00 |
| ENV TF 2004 | 1 125 000 | 0.00 | 0.00 | 83 333 | 0.00 | 0.00 |
| ENV Total 2001 - 2004 | 11 553 785 | 67.94 | 39.24 | 899 333 | 40.87 | 24.24 |
| REG FM 2001 | 14 200 000 | 92.62 | 86.77 | 6 388 000 | 97.31 | 102.93* |
| REG FM 2002 | 13 250 000 | 98.77 | 28.90 | 4 828 000 | 97.62 | 46.38 |
| REG FM 2003 | 15 000 000 | 0.01 | 0.00 | 4 930 000 | 0.00 | 0.00 |
| REG Total 2001 - 2004 | 42 450 000 | 61.81 | 38.05 | 16 146 000 | 67.69 | 54.59 |
| CBC FM 2001 | 10 200 000 | 79.19 | 77.99 | 5 469 000 | 76.21 | 73.76 |
| CBC FM 2002 | 12 000 000 | 92.86 | 10.50 | 5 060 086 | 82.45 | 0.00 |
| CBC FM 2003 | 13 400 000 | 2.76 | 0.00 | 2 100 000 | 0.00 | 0.00 |
| CBC Total 2001 - 2004 | 35 600 000 | 55.03 | 25.88 | 12 629 086 | 51.59 | 24.95 |
| HRD FM 2001 | 13 150 000 | 93.66 | 46.69 | 10 475 000 | 97.81 | 30.05 |
| HRD FM 2002 | 4 810 000 | 75.48 | 57.66 | 1 650 000 | 96.77 | 77.58 |
| HRD FM 2003 | 8 700 000 | 10.33 | 6.01 | 1 754 000 | 8.50 | 0.00 |
| HRD TF 2004 | 1 190 000 | 0.00 | 0.00 | 100 000 | 0.00 | 0.00 |
| HRD Total 2001 - 2004 | 27 850 000 | 60.49 | 33.88 | 13 979 000 | 85.78 | 31.67 |

*Additional funding for supplementary works was secured by the state budget and the final beneficiary.

## Operational Performance of the SMSCs in €*

| Monitoring Sector | Amount of Funds evaluated | Highly Satisfactory | % | Satisfactory | % | Unsatisfactory | % | Highly Unsatisfactory | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| JHA | 25 144 997 | 0 | 0.0 | 19 164 997 | 76.2 | 5 980 000 | 23.8 | 0 | 0.0 |
| JHA SMSC | 25 144 997 | 0 | 0.0 | 19 164 997 | 76.2 | 5 980 000 | 23.8 | 0 | 0.0 |
| INT | 18 265 000 | 170 000 | 0.9 | 17 345 000 | 95.0 | 750 000 | 4.1 | 0 | 0.0 |
| AGR | 27 881 000 | 1 636 000 | 9.2 | 14 895 000 | 83.3 | 1 350 000 | 7.6 | 0 | 0.0 |
| ENV | 10 379 143 | 1 250 000 | 12.0 | 8 539 143 | 82.3 | 590 000 | 5.7 | 0 | 0.0 |
| INT SMSC | 46 525 143 | 3 056 000 | 6.6 | 40 779 143 | 87.6 | 2 990 000 | 6.4 | 0 | 0.0 |
| REG | 33 200 000 | 0 | 0.0 | 23 000 000 | 69.3 | 10 200 000 | 30.7 | 0 | 0.0 |
| CBC | 22 200 000 | 0 | 0.0 | 0 | 0.0 | 18 000 000 | 81.1 | 4 200 000 | 18.9 |
| HRD | 26 660 000 | 0 | 0.0 | 12 500 000 | 46.9 | 14 160 000 | 53.1 | 0 | 0.0 |
| ESC SMSC | 82 060 000 | 0 | 0.00 | 35 500 000 | 43.3 | 42 360 000 | 51.6 | 4 200 000 | 5.1 |
| Total | 153 730 140 | 3 056 000 | 2.0 | 95 444 140 | 62.1 | 51 330 000 | 33.4 | 4 200 000 | 2.7 |

* Figures come from the most recent interim evaluation reports.

| Highly Satisfactory | The programmes reviewed are expected to achieve or exceed all the objectives set during lifetime. |
| --- | --- |
| Satisfactory | The programmes reviewed are expected to largely achieve the objectives set during their lifetime. |
| Unsatisfactory | The programmes reviewed are not expected to achieve most of the objectives set during their lifetime. |
| Highly Unsatisfactory | The programmes reviewed are not expected to achieve any of the objectives set during their lifetime. |

## Major Problems

- Shortcomings in project design.

- Immeasurable indicators of achievement.

- Lack of professional capacity to draft project proposals and prepare tender documentation because of high staff turnover adversely affecting any attempts to develop and sustain their skills and experience.

- Basic conditionality for smooth project implementation (e.g. land ownership, building permits) not secured in time.

- Too long time gap between programming and actual implementation and subsequent change in project circumstances or beneficiary’s needs.

- Late forwarding of tender documentation from the line ministries to the Central Finance and Contracting Unit.

- Problems with transfer to new procurement rules (PRAG – GGAPP – national legislation) in the year 2004.

- Last minute contracting and its adverse consequences for proper implementation particularly for absorption capacity.

- Lack of suitable project alternatives for reallocation.

- Insufficient inter-institutional co-ordination and communication.

- Some project monitoring reports issued by line ministries are reduced to passive reporting without identifying problems and suggesting appropriate remedial measures.

- Awareness of high managerial level of key findings and recommendation of the evaluation process should be increased.

###### Key Steps Taken

- Training on Transition Facility programming with a special focus on the development of skills and competencies in Institution Building project design delivered in December 2004. Moreover, special attention is also being paid to formulation of indicators of achievement to make them quantified, measurable, time bound and thus usable for monitoring and evaluation purposes.

- Topping up of public officials' salaries administering EU-funded projects to keep experienced and skilled staff.

- Training on new procurement rules delivered to line ministries to increase their technical knowledge on new tender docomunentations' templates. However, the national contracting legislation seems to have even lengthier procedures in comparison with the PRAG/GGAPP. The risk of last minute contracting or non-contracting remains very high.

- To eliminate any loss of funds critical assessment of risky projects is done continuously at the contracting meetings where all implementing agencies (IA), National fund (NF) and Aid Coordination Unit (ACU) are present. Beneficiaries are also encouraged to consider reallocation of funds where the possibility to contract them is very low. Moreover, all programmes/projects are monitored at monthly meetings to detect a need for project fiche modification in time.

- The Aid Coordination Unit keeps organising training on monitoring procedures and report compilation for line ministries.

- In the case when more than one ministry is involved in the project implementation beneficiaries ought to organize common Steering Committees in order to ensure close coordination of project activities.

- The key evaluation findings and recommendations are delivered to the attention of ministers or state secretaries via the Ministerial Council for EU Affairs in order to increase the political awareness of the problems in Phare and Transition Facility.

## Co-financing Status

National co-financing is provided by national public funds in compliance with Memorandum on the Principles for Phare Co-financing Requirements of 11 September 2002 and project-fiches. Based on EC requirements the information on co-financing is included to the Request for Payments. Information on co-financing is delivered by implementing agencies (or by line ministries through implementing agency). Overall system for co-financing and responsibilities for implementation is laid down in Guidelines on management of financial means during the implementation of Phare programme and Transition Facility as well as in the resolution of the Government of the Slovak Republic Concept on funding of the projects endorsed by the pre-accession Funds, Transition Facility and Cohesion Fund during the years 2004 – 2006. Both of them have been approved by the Government of the Slovak Republic and later on promulgated on the web site of the Ministry of Finance of the SR

Expenditures on signed financing memoranda are includes to the state budget and they are planned within multiannual budgeting. Funds for co-financing from state budget are publicised annually in the Act on State Budget what ensures a high level of transparency of information on national co-financing of the projects implemented together with EC contribution. The Ministry of Finance releases co-financing through National Fund based on Implementation Agency’s request.

Since 1 January 2004 there have been two types of co-financing possible in Phare and Transition facility project implementation – joint and parallel co-financing. Following the European Commission's request to implement join co-financing for the 2001, 2002 and 2003 projects, the National Fund has introduced the necessary system changes to meet this requirement. Parallel co-financing has to be justified enough and is endorsed by the Commission only in exceptional circumstances.

Parallel co-financing – the different project parts are financed from different sources according to the project specification at different time. Besides the state budget, the co-financing may come also from other sources (final beneficiary) and may have various forms of financial contribution, or in kind co-financing. While the Phare contribution to the project is contracted and the payments are executed by the respective implementing agency, the co-financing part is usually contracted and executed by the final beneficiary.

Joint co-financing – the total project cost is divided between the co-financing partners according to the proportion established in the project fiche. The payments are disbursed from various sources at the same time according the specified proportion. Implementing agency pays the full amount of the invoices to the contractor, based on a bilateral agreement between the contractor and the implementing agency. The agency receives the EU and co-financing funds upon request from the National Fund according to the Financing Agreement. In some cases, the final beneficiary may also participate in the project co-financing. In these cases, the final beneficiary transfers the corresponding co-financing amount into the implementing agency's bank account in accordance with the implementation agreement, a document signed by the final beneficiary and the agency.